## Sheet1
Risk | Risk Resolution Measures | Justification
1. Gold plating (adding features that are not required) | Make sure all features are accounted for with time and make changes to agile points if needed every time a new feature is added or designed. | With making all features and designs accounted for this will prevent to bring to light any feature that is not needed or needs extra time for the project
2. Unrealistic budget | With it being for a school the budget might be low or tight. Limit changes or unneccesary features and make sure timelines are met. | Ensuring that the timelines are constantly brought up and looked at to make sure time and budget doesn't go over will help the project stay on the tight budget.
3. Developing wrong user interface | Everytime a new user interface is designed get the approval of most of the team or maybe the end user/customer. | To eliminate the posibility of creating the wrong user interface or one that is wrong for the end user the developers need to check with the users frequently
4. Database connections | Since most of the project relies on the information sending and receiving through databases. Ensure the code that connects the databases to the user and user interface is solid and has fail checks and fail safes | Constantly putting in fail safes for if the connection to the databases go down will make the whole end project better
5. Langauge translation/ wording | Since this is for overseas student programs there could be some misunderstanding parts of the forms or proceedure. Make sure to get approval from multiple overseas faculty before finalizing wording and interfaces. | Although not every language can be accounted for the developers should make sure the languages that are prominent in the countries that the programs are offered should be a priority to offer.